## Sheet1
DRIFT WOOD-E
| Project Start Date: | 2024-11-15 | [20 empty] | December | [31 empty] | January
| Project Name: | Campus Safety App | time axis 2024-11-15 to 2025-07-05
# | Activity | Start | End | Days | Status | %Done
1 | Planning & Requirement Gathering | [5 empty] | 2024-11-15: Planning and Requirement Gathering
2 | Gather and document business requirements from stakeholders | 2024-11-15 | 2024-11-16 | 2 | Complete | 100% | bar: 2024-11-15 to 2024-11-16
3 | Define project scope and objectives | 2024-11-16 | 2024-11-16 | 1 | Complete | 100% | bar: 2024-11-16
4 | Identify project resources, timeline, and budget | 2024-11-17 | 2024-11-17 | 1 | Complete | 100% | bar: 2024-11-17
5 | Create project communication plan | 2024-11-18 | 2024-11-18 | 1 | Complete | 100% | bar: 2024-11-18
6 | Organize project kick-off meeting | 2024-11-19 | 2024-11-19 | 1 | Complete | 100% | bar: 2024-11-19
7 | Project requirements and scope finalized | 2024-11-20 | 2024-11-20 | 1 | Complete | 100% | bar: 2024-11-20
5 | Design | [5 empty] | 2024-11-24: Planning Phase
6 | Create wireframes or prototypes (UI/UX | 2024-11-21 | 2024-11-25 | 5 | Complete | 100% | bar: 2024-11-21 to 2024-11-25
7 | Develop technical design documents (architecture, database) | 2024-11-26 | 2024-11-30 | 4 | Complete | 100% | bar: 2024-11-26 to 2024-11-30
8 | Review design with stakeholders and gather feedback | 2024-12-01 | 2024-12-04 | 4 | Complete | 100% | bar: 2024-12-01 to 2024-12-04
9 | Design approved by stakeholders | 2024-12-05 | 2024-12-07 | 2 | Complete | 100% | bar: 2024-12-05 to 2024-12-07
10 | Wireframes, UI/UX, and database schema approved | 2024-11-22 | 2024-11-22 | 1 | Complete | 100%
11 | Development | [5 empty] | 2024-12-10: Development Phase
12 | Set up development environment | 2024-12-08 | 2024-12-12 | 5 | Complete | 100% | bar: 2024-12-08 to 2024-12-12
14 | Develop front-end and back-end components | 2024-12-13 | 2024-12-19 | 7 | Complete | 100% | bar: 2024-12-13 to 2024-12-19
15 | Integrate front-end and back-end | 2024-12-20 | 2024-12-26 | 7 | Complete | 100% | bar: 2024-12-20 to 2024-12-26
16 | First integrated version ready for testing | 2024-12-27 | 2024-12-28 | 2 | Complete | 100% | bar: 2024-12-27 to 2024-12-28
17 | Geolocation Sharing Feature | 2024-11-28 | 2024-11-29 | 2 | Complete | 100% | bar: 2024-11-28 to 2024-11-29
18 | Core functionalities implemented and integrated | 2024-11-30 | 2024-11-30 | 1 | Complete | 100% | bar: 2024-11-30; 2025-01-01
19 | Testing & QA | [5 empty] | 2025-01-01: Testing and QA
21 | Develop and execute test cases (unit, integration, UAT) | 2024-12-29 | 2025-01-02 | 5 | Complete | 100% | bar: 2024-12-29 to 2025-01-02
22 | Track and resolve bugs | 2025-01-03 | 2025-01-06 | 4 | Complete | 100% | bar: 2025-01-03 to 2025-01-06
23 | Perform regression testing | 2025-01-07 | 2025-01-09 | 3 | Complete | 100% | bar: 2025-01-07 to 2025-01-09
24 | All critical bugs resolved and UAT approved | 2025-01-10 | 2025-01-11 | 2 | Complete | 100% | bar: 2025-01-10
25 | Deployment | [5 empty] | 2025-01-13: Development
26 | Develop deployment plan and set up production environment | 2025-01-12 | 2025-01-13 | 2 | Complete | 300% | bar: 2025-01-11 to 2025-01-12
25 | Deploy the product to the live environment | 2025-01-14 | 2025-01-15 | 2 | Complete | 100% | bar: 2025-01-13 to 2025-01-14
26 | Verify deployment and ensure system stability | 2025-01-16 | 2025-01-17 | 2 | Complete | 100% | bar: 2025-01-15 to 2025-01-16
27 | Deployment to live environment completed successfully | 2025-01-18 | 2025-01-18 | 1 | Complete | 100% | bar: 2025-01-17
28 | POST-LAUNCH SUPPORT | [5 empty] | 2025-01-22: Post-Launch Support
29 | Monitor system performance and resolve any post-launch issues | 2025-01-05 | 2025-02-19 | 45 | Complete | 100% | bar: 2025-01-18 to 2025-02-20
30 | Provide ongoing user support | 2025-02-20 | 2024-04-05 | 45 | Complete | 100% | bar: 2025-02-21 to 2025-04-05
31 | Collect feedback for future improvements | 2025-04-06 | 2024-05-20 | 45 | Complete | 100% | bar: 2025-04-06 to 2025-05-20
32 | Post-launch review completed and maintenance plan established | 2025-05-21 | 2025-07-05 | 45 | Complete | 100% | bar: 2025-05-21 to 2025-07-05
Statuses
Not Started
In Progress
Blocked
Complete
Formulas:
End = [Start]+1
Start = [Start, row above]+1